## Slide 1: Transplant first: Addressing inequality of access to renal transplantation across the West Midlands
Kerry Tomlinson on behalf of sponsor group
UKKW 2017

## Slide 2: Content
Background
Is it working
What we did
Lessons learnt
Next steps and KQUIP roll out

## Slide 3: Background: identifying the problem
  UK RR 2014 report median time to listing
  488, 598, 641, (683), 712, 765, 787, 867

## Slide 4: Project Background
Proposed to and adopted by West Midlands Cardiovascular Strategic Clinical Network (Renal Expert Advisory Subgroup)
Aims to:-
  lead to a progressive reduction in the excessive waiting times to renal transplantation in the West Midlands
  Improve access to renal transplantation for all patients in the west midlands
Full mandate and documents on website www.wmscnsenate.nhs.uk
The project will not disadvantage existing dialysis or transplant listed patients
www.thinkkidneys.nhs.uk/kquip/transplant-first/

## Slide 5: What will we achieve? (Is it working?)
West Midlands will achieve >95% patients starting RRT with a transplant status
The West Midlands will have the highest rate of pre-emptive listing in the UK
The wait for deceased donor kidneys in the West Midlands will be in line with the national average or better
We will be in the top 50% of transplant units for pre-emptive transplants
95% of all CKD 5 patients will have a documented transplant decision
> 50% of patients will be listed pre-emptively

## Slide 6: % of CKD 5 patients with recorded transplant status on IT system
Chart: 
| Q42015 | Q32016
Wolverhampton | 0 | 95
Shrewsbury | 0 | 85
HEFT | 100 | 100
Coventry | 0 | 17
QE | 74 | 98
Dudley | 0 | 100
Stoke | 48 | 85
Mean | 31.7143 | 82.8571

## Slide 8: UHB listings from all units
Chart: 
| 2013 | 2014 | 2015 | 2016
pre-emptive | 52 | 48 | 58 | 77
 | 140 | 143 | 125 | 112

## Slide 9
Median days from listing to transplant | UHB | Coventry
2016 | 1121 | 1008
2015 | 1542 | 1056

## Slide 10
Chart: 
| Q12016 | Q22016 | Q32016 | Q42016 | Q12017
Pre-dialysis | 17 | 10 | 5 | 21
On Dialysis | 56 | 49 | 42 | 35
Chart: 
| Q12016 | Q22016 | Q32016 | Q42016 | Q12017
Pre-dialysis | 17 | 10 | 5 | 21
On Dialysis | 56 | 49 | 42 | 35
Self reported pre-emptive kidney alone transplant rates (note includes transplants outside the region)

## Slide 11: What did we do?
Launch event
July 2015
Pathway Redesign 1
Pathway redesign 2
Audit/Education event Jul 2016
Audit Education event July2017
Project events
Transplant Units
Renal Units
Patients and carers
External experts
SCN/KQUIP

## Slide 12
Launch event
July 2015
Pathway Redesign 1
Pathway redesign 2
Audit/Education event Jul 2016
Audit Education event July2017
Patient Voice
Honest discussion
BMI debate
Valuable time
Quick Wins
Early agreement
Handover points
Sponsor team meetings, conference calls, working with RR, subgroup meetings, contact with units etc
Cardiac catheter abstract
Unit feedback

## Slide 13: Project Structure
KQUIP
UKRR
ODT
NICE
Taking organ transplantation to 2020
LDKT 2020
•
I
de
ntif
y
da
t
a
r
eq
ui
r
ed
,
i
t
s
sou
r
ce
an
d obt
ai
n
ag
r
ee
m
en
t
t
o
sha
r
e
da
t
a
across
t
he
r
eg
i
on
•
A
g
r
ee
f
orm
att
i
ng
an
d r
eg
ul
arity
of
r
ep
ort
i
ng
,
e.g
.
q
ua
r
t
erly
au
di
t
an
d
f
ee
db
ack
of
t
otal
t
r
an
spl
an
t
,
l
i
v
e
do
no
r
,
de
cea
sed
do
no
r
an
d
pre
-
empt
i
v
e
t
r
an
spl
an
t
l
i
st
i
ng
r
ates
at
ea
ch
un
i
t
•
I
de
ntif
y
r
ep
osi
t
ory
f
or
da
t
a
•
D
ev
el
op
i
nf
r
astr
uct
ure
f
or
au
di
t
,
r
ev
i
ew
an
d
r
ep
ort
i
ng
,
e.g
.
R
C
A
an
d
au
di
t
of
al
l
pa
t
i
en
t
s
st
art
i
ng
R
R
T
w
i
t
ho
ut
a
t
r
an
spl
an
t
l
i
st
st
atus
D
ata,
m
ea
sures
an
d
i
m
pl
ement
atio
n
(K
err
y
T
omli
nso
n )
•
I
de
nti
f
y
cl
i
ni
ca
l
stand
ards
an
d
g
ui
de
l
i
ne
s nee
de
d
t
o
i
mprov
e acc
es
s
t
o
t
r
an
sp
l
an
t
e.g
.
w
r
i
t
t
en
ac
ce
ptan
ce
cr
i
t
eria
f
or
acce
ptance
on
k
i
dn
ey
t
r
an
spl
an
t
w
ai
t
i
ng
l
i
st
•
I
de
ntif
y
w
he
r
e document
s
al
r
ea
dy
av
ai
l
ab
l
e
an
d
i
de
ntif
y
g
ap
s,
de
v
el
op
i
ng
r
eg
i
on
al
st
an
da
r
ds
an
d
g
ui
de
l
i
ne
s
as r
eq
ui
r
ed
S
t
an
da
r
ds
an
d g
ui
de
l
i
ne
(N
i
ck
I
nston )
•
M
ap
t
he
curr
en
t
pa
t
i
en
t
pa
t
hw
ay
s
by
r
en
al
un
i
t
across
t
he
r
eg
i
on
•
Co
-
de
si
g
n
ex
empl
ar
pa
t
hw
ay
s
w
i
t
h pat
i
en
t
s
an
d
cl
i
ni
ci
an
s
i
n li
ne
w
i
t
h ag
r
ee
d
st
an
da
r
ds
an
d g
ui
de
l
i
ne
s
P
athw
ay
s
(
K
err
y
T
omli
nso
n)
•
C
ol
l
ate
i
nf
orm
atio
n
use
d
across
t
he
r
eg
i
on
an
d
up
l
oa
d t
o
S
C
N
w
eb
si
t
e
•
I
de
ntif
y
an
y
g
ap
s
an
d
de
v
el
op
f
urt
he
r
r
eso
urces
as r
eq
ui
r
ed
P
atie
nt
i
nf
orm
atio
n
(
H
el
en
S
po
on
er)
•
I
de
ntif
y
t
r
ai
ni
ng
ne
ed
s
of
al
l
proj
ect
pa
r
t
i
ci
pa
nts,
e.g
.
Q
I
f
or
un
i
t
l
ea
ds and pat
i
en
t
r
ep
r
ese
ntat
i
v
es
•
S
ou
r
ce/desi
g
n,
cost
an
d
de
l
i
v
er
t
r
ai
ni
ng
•
E
st
ab
l
i
sh
actio
n le
arni
ng
sets
•
D
esi
g
n
f
i
r
st
t
r
an
spl
an
t
ed
uca
t
i
on
an
d audi
t
ev
en
t
t
o
sha
r
e
be
st
pract
i
ce,
f
or
r
ol
l
-
ou
t
an
nu
al
l
y
t
he
r
ea
f
t
er
E
du
catio
n
(
C
eci
l
y
H
ol
l
i
ng
w
ort
h)
P
a
r
t
n
e
r
s
h
i
p
B
o
a
r
d
S
p
o
n
s
o
r
T
e
a
m
Donor Patient View

## Slide 14: Data : Enhanced Dashboard (It’s taken ages so I am telling you about it whether you like it or not!)

## Slide 15: Data: transplant listing

## Slide 16: Barriers to using data effectively
Me/Time
It is extremely difficult to develop data set (anyone starting project now wont have to!)
    Definitions
    Collection
    Collation
Tendency to justify exceptions (balance between wanting data to look good and using it to improve)
Separation between people filing in data and those doing project
It only works if you use it locally

## Slide 17: Cut and Paste: Argghhhh!!!
Active on list
Suspended from list
Unsuitable
Working up or under discussion
No documented decision

## Slide 18: Transplant status from Enhanced dashboard
Chart: 
| Q4 2015 | Q1 2016 | Q2 2016 | Q3 2016 | Q4 2016 | Q1 2017
Unsuitable | 74 | 74 | 105 | 114 | 58 | 94
Suspended from list | 12 | 6 | 8 | 13 | 9 | 3
Active on list | 19 | 22 | 18 | 20 | 15 | 19
Working up or under discussion | 24 | 34 | 27 | 33 | 24 | 18
No documented decision | 25 | 33 | 24 | 27 | 19 | 14
Invalid category | 0 | 0 | 0 | 13 | 0 | 0

## Slide 19: Lessons learnt from data
Transferable causes for missing listing:
  Failing transplants
  Predictable but rapidly declining patients
  Different approaches to cardiac angiography pre-dialysis
Local causes for missing listing :
  Specific clinics (e.g. diabetes multi-disciplinary)
  Different feeder hospitals
  Other reasons that will be apparent locally
It only works if you use it locally

## Slide 20: Reason given why patients were not listed pre-emptively
Chart: 
| Delays in system | Referred when eGFR < 15 | Referred within a year of predicted RRT | Patient DNA on >3 occassions | Medically complex | Unplanned start | Patient choice | Unsuitable became suitable | Transferred in | No data
Q12017 | 3 | 0 | 2 | 2 | 13 | 3 | 1 | 6 | 3 | 2

## Slide 21: Positive stories
  Better collaborative working to improve patient experience
Working with other units to improve transplantation and work together for a better patient experience
Improving transplant profile for staff and patients
Better data to influence decisions
  Highlighted pathway delays and led to re-design
We now have a Transplant Coordinator in post

## Slide 22: How sponsor team have found it
Time needed can’t be overestimated
Project support is key (Changed from SCN to KQUIP half way through)
Different Transplant Unit approaches to involvement
Have to rely on engagement of units and work hard to keep enthusiasm
Patient engagement is difficult both in breadth and sustainability
Data collection is very difficult
Getting feedback can be difficult
On-going need for human interactions and mediation

## Slide 23: Barriers from Unit perspective
Lack of time for individual units to discuss changes
Consultants
Staffing shortages
Software barriers
Would like more personalized input
Would like more interaction
Change in unit personnel
Role of ongoing QI education

## Slide 24: Next steps
TF rollout through KQUIP
Producing “How to Guide” and attending regional meetings
More work to access national data more easily
Dovetailing with other sources of information
  ATTOM
  Renal Registry
Increasing momentum e.g. GIRFT

## Slide 25
Thank you to all patients, carers, kidney unit staff, registry staff etc. who are working on the project
West Midlands Clinical Network