## Slide 1: KQUIP MAGIC PROJECT
Analysis of data Jan- June 2020
Name: Emily Luab Unit : SDU
Date: 06.07.20

## Slide 2: Problems / Trends
Patient’s admitted to other units coming back with different needling technique for example from Rope Ladder to area.

## Slide 3: Lessons learned and how problems were resolved
Informed access coordinator to discuss
Educate patient to know or familiarise them with what needling technique they are using so they could inform the staff.
Re start again to go back to the old needling technique they had prior to admission

## Slide 4: What are we doing to sustain the project
By adhering to our unit’s Magic objective of No Area Puncture.
Staff education
= 100% staff completed the Magic E-Learning
= 100% staff including new starter completed Cannulation Skills Competency Pack
= ensuring all new staff will complete the Magic E-Learning and Cannulation Skills Competency Pack within their probationary period.
Patient Education:
= Each patient is given information about magic and needling technique.
= Given pocket information on how to take care of their AVF and what to do during bleeding at home.
= Given and instructed on how to use ring cap to stopped bleeding at home.
= Showed and explained to them about the Magic posters on Love my Buttonhole, Rope Ladder, Needling Technique and was given the pocket version of their needling technique.
= Displayed Magic posters on our board in waiting area.
= Pre and Post evaluation almost done.
Monthly audit and input data on Life QI